## Portal Checklist
Partner Portal Reseller Program Checklist
| Category |  |  |  |  | Time Frame | Schedule | Assigned To | Notes
Status | Program Definition & Setup
|  | Define program (levels, agreement, policies) |  |  |  | 40 min
Setup Portal
|  |  | Sign up for ISP (Bluehost recommended) |  |  | 10 min
|  |  | Create domain name (CompanyPartners.com) |  |  | 10 min
|  |  | Install Wordpress (fresh install) |  |  | 30 min
|  |  | Clone portal |  |  | 20 min
Note: please do not modify anything until setup is complete & backed up
|  |  | Update all plugins |  |  | 5 min
|  |  | Remove plugins that don't apply (LeadSmart, WP Engine) |  |  | 5 min
|  |  |  | LeadSmart |  | 1 min
|  |  |  | WP Engine |  | 1 min
|  |  | Decide & submit channel manager name, title, phone & email (partners@company.com) |  |  | 5 min |  |  | Do not use actual email (use a "role-based" partners@), then have IT redirect it to your personal email.
|  |  | Personalize |  |  | 1 hour
|  |  |  | Resize and add logo to theme |  | 10 min
|  |  |  | Add company Favicon |  | 5 min
|  |  |  | Search & Replace |  |  |  |  | Use Tools/ Better Search & Replace. Remember to untick the last box to complete the replacement.
[5 empty] | Channel Manager Name | 5 min
[5 empty] | Phone | 5 min
[5 empty] | Email | 5 min
[5 empty] | Title | 5 min
|  |  |  | Add photo of Channel Manager |  | 10 min |  |  | A square photo 80x80 is the default size
|  |  | Submit preferred company address |  |  | 5 min
|  |  | Update address on footer and contact us page |  |  | 5 min |  |  | Go to Appearance / Widgets / Footer 1-4 to change contact info
|  |  | Add logo & customize LoginPress (colors, background) |  |  | 1 hour
|  |  | Setup captia w/Google |  |  | 15 min
|  |  | Setup Google maps (create project, then add maps info) |  |  | 20 min |  |  | See detailed instruction in documentation
|  |  | Add Captia to Gravity Forms |  |  | 5 min
|  |  | Add Captia to Membership Pro |  |  | 5 min
|  |  | Add Server Code to Maps |  |  | 5 min
Change Settings Master email (should be partners@company.com)
|  |  | Review & edit every applicable form | [5 empty] | Do not remove until you understand profiling
Contact Me
Deal Register
MDF Request form
NFR Quiz
Place Order
Referral Form
Referral Partner Application
Reseller Application
Need other forms? Distributor (so they are in the system)
|  |  | Test every form (consider SMTP email - if not setup by ISP) | [5 empty] | PHP is the default WordPress email--but may have to use SMTP for better deliverability
Update initial newsletter copy
Chat Setup
Switch user (login to Zendesk for free account, use new login)
|  |  |  | Edit in Plugin or in Widgets area |  |  |  |  | Found in Custom HTML section of Footer 4
|  |  |  | Download and setup mobile Zendesk app |  |  |  |  | Allows you to see who is on your site, plus you can support via mobile text
Confirm emails and chat messages are arriving
Affiliate Setup
|  |  |  | Add URL to the WPAffiliate site - register URL |  |  |  |  | Site Licence resides with Chanimal - site must be added to activate software
Determine program elements
Commission
How to pay
System to pay
Privacy policy
Create banner
Edit copy sections
Create affiliate sample landing page
Integrations
CRM / Marketing Automation
Install plugin
Map fields
Test bi-directional
Note: some plugins may require 3rd party upgrades that are not part of the normal portal
Other chat, reporting
Test portal (ALL forms, all systems, logins, everything)
Back it up (Updraft Plus - Settings)
Add portal content (PowerPoint, Comp Matrix, Price List, White Papers, etc.)
Put a link to reseller portal / application from main site - ready to recruit
Content updates
Reseller agreement
Affiliate agreement
|  |  | Review & edit every policy on every page |  |  | 2 hours
|  | Create outstanding deliverables for portal |  |  |  | Varies
|  |  | Competitive Matrix |  |  | 3 weeks |  |  | If don't have one
|  |  | PowerPoint |  |  | 1 day - 1 week |  |  | Time dependant on persuasive doc
|  |  | 25/50/100 word description |  |  | 2 hours
|  |  | Market Info |  |  | 2 hours
|  |  | Logo, graphics |  |  | 30 min
|  |  | Price list (PDF) |  |  | 1 hour
|  |  | Create product demo script |  |  | 4 hours
|  |  | Other (white papers, case studies, videos) |  |  | Varies
|  | Review EVERY page of portal site - confirm it is complete |  |  |  | 1 hour
|  | Determine reseller margin & how will get paid |  |  |  | 2 hours
|  | Confirm the system and process for partner payments |  |  |  | 1 hour
|  | Create reseller approval email |  |  |  | 1 hour
|  | Create recruiting emails (for previous interest, new, competititors) |  |  |  | 2 hours
|  | Create orientiaton demo script |  |  |  | 5 min
|  | Determine NFR process (how to get partner license #'s) |  |  |  | 1 hour
Portal Training
Portal documentation overview - please read entire document (you will live in this portal)
Admin Section (review each section so you know where to go for help)
|  |  | Wordpress overview & training (if don't know how to edit) - YouTube |  |  | 3 hours
|  |  | Know how to add reseller to portal (add User, configure User) |  |  | 30 min
|  |  | Know how to manage forum |  |  | 1 hour
|  |  | Can add a page, set permissions |  |  | 30 min
|  |  | Can add a contact to reseller locator |  |  | 15 min
Take basic tutorial for LearnPress
|  | Finalize Reseller Follow-up Worksheet |  |  |  | 30 min
Set up new resellers
|  |  | Get NFR information |  |  | 15 min
|  |  | Add reseller to portal (will send out email) |  |  | 15 min
|  |  | Determine webinar date |  |  | 15 min
|  |  | Edit approval email (NFR, password, webinar date) and send |  |  | 15 min
Enablement
|  | Create reseller SEO - landing page template (basic, then advanced) |  |  |  | 3 hours
|  | Create reseller email template |  |  |  | 3 hours
|  | Repurpose the lead referral template |  |  |  | 2 hours
|  | Setup marketing meeting with reseller |  |  |  | 15 min each
|  | Conduct marketing meeting (setup 3 promos (setup promo calendar)) |  |  |  | 20 min each
|  | Conduct marketing meeting - SEO landing page template, email campaign |  |  |  | 1 hour setup
2nd Setup
|  |  | Confirm reseller has product listed on website |  |  | 10 min
|  |  | Add reseller to reseller locator (within portal) |  |  | 10 min
|  |  | Send email to reseller confirming now listed in locator |  |  | 10 min
|  | Create thank you email - for reseller's first sale, send to reseller |  |  |  | 10 min
|  | Create thank you email for 2nd sale - send to reseller |  |  |  | 10 min
|  | Create newsletter template, send monthly newsletter (informatl) |  |  |  | 1 hour
|  | Setup levels, certification, quotas |  |  |  | 6 months later
Define reseller levels (usually at 6 month mark)
|  |  |  | Review existing reseller sales, determine break points |  | 1 hour
Define certification program
|  |  |  | Review reseller FAQs, additional training areas |  | 2 hours
|  |  |  | Determine how to train/certifiy resellers |  | 1 hour
|  |  |  | Determine systems to use (LMS) |  | 1 hour | Learn
|  |  |  | Create training material (PowerPoint, manuals) |  | 3 months
|  |  | Create reseller levels and certification policies |  |  | 3 months
|  |  | Create reseller email to announce program |  |  | 1 hour
|  |  | Setup meeting with ALL partners (1 on 1, group webinars) to review new levels and certification |  |  | 1 hour
|  |  | Conduct partner meetings (with EVERY partner) - use worksheet to confirm attendance |  |  | 1 hour

## Program Checklist
Reseller Program Checklist
| Category |  |  |  | Time Frame | Schedule | Assigned To | Notes
Status | Program Definition & Setup
|  | Define program (levels, agreement, policies) |  |  | 1 hour
Setup Portal
|  |  | Install Wordpress (fresh install) |  | 30 min
|  |  | Clone portal |  | 45 min
|  |  | Personalize - logo, etc. |  | 1 hour
|  |  | Setup emails and phone (partners@company.com), separate phone line |  | 30 min
|  |  | Test portal (ALL forms) |  | 30 min
|  | Setup policies (review & edit every page of portal) |  |  | 2 hours
|  | Create SaaSMAX Profile (if applicable) and Ideal Partner Configuration |  |  | 2 hours
|  | Create outstanding deliverables for portal |  |  | Varies
|  |  | Competitive Matrix |  | 3 weeks |  |  | If don't have one
|  |  | PowerPoint |  | 1 day - 1 week |  |  | Time dependant on persuasive doc
|  |  | 25/50/100 word description |  | 2 hours
|  |  | Market Info |  | 2 hours
|  |  | Logo, graphics |  | 30 min
|  |  | Price list (PDF) |  | 1 hour
|  |  | Create product demo script |  | 4 hours
|  |  | Other (white papers, case studies, videos) |  | Varies
|  | Review EVERY page of portal site - confirm it is complete |  |  | 1 hour
|  | Determine reseller margin & how will get paid |  |  | 2 hours
|  | Confirm the system and process for partner payments |  |  | 1 hour
|  | Create reseller approval email |  |  | 1 hour
|  | Create recruiting emails (for previous interest, new, competititors) |  |  | 2 hours
|  | Create orientiaton demo script |  |  | 5 min
|  | Determine NFR process (how to get partner license #'s) |  |  | 1 hour
|  | Confirm the WordPress master user email is switched to your partner@ email |  |  | 5 min
|  | Confirm Zendesk chat has been switched to partner@email - shows traffic at portal site |  |  | 10 min
|  | Put a link to reseller portal / application from main site - ready to recruit |  |  | 10 min
Recruiting
|  | Complete SaaSMAX IPC (Ideal Partner Configuration) |  |  | 15 min |  |  | info.saasmax.com/ideal-partner-configuration-form
Database
|  |  | Compile list of any previously interested partners |  | 1 hour
|  |  | Compile Chanimal database |  | 1 hour
|  |  | Compile competitors resellers (internal & Navin) |  | 1 week |  |  | A counter-strike - weakens their program, strengthens yours
|  |  |  | Finalize reseller database fields (Chanimal sample) | 3 hours
Systems
|  |  | Determine CRM systems or spreadsheet |  | 1 hour
|  |  | Mass email system - select & setup |  | 2 hours
|  |  | Import database(s) into email system |  | 1 hour
|  |  | Setup recruiting email template(s) |  | 30 min
|  |  | Call our phone numbers, send ourselves emails - confirm they are all active |  | 15 min
|  |  | Confirm channel people are getting the emails from the partner FORMS |  | 15 min
Email campaign
|  |  | Determine when it will go out (days and times (typically work hours)) |  | 30 min
|  |  | Start first email |  | 30 min
|  |  | Clean out bounce backs, remove names, applied/responded |  | 2 hours
|  |  | Start 2nd email |  | 30 min
|  |  | Clean out bounce backs, remove names, applied/responded |  | 1 hour
|  |  | Start 3rd email |  | 30 min
|  |  | Clean out bounce backs, remove names, applied/responded |  | 1 hour
Portal Training
|  |  | Wordpress overview & training (if don't know how to edit) - YouTube |  | 3 hours
|  |  | Know how to add reseller |  | 30 min
|  |  | Know how to manage forum |  | 1 hour
|  |  | Can add a page, set permissions |  | 30 min
|  |  | Can add a contact to reseller locator |  | 15 min
|  | Finalize Reseller Follow-up Worksheet |  |  | 30 min
Set up new resellers
|  |  | Get NFR information |  | 15 min
|  |  | Add reseller to portal (will send out email) |  | 15 min
|  |  | Determine webinar date |  | 15 min
|  |  | Edit approval email (NFR, password, webinar date) and send |  | 15 min
Orientation
|  | Learn the product |  |  | 6 hours
|  | Learn the product demo script |  |  | 3 hours
|  | Learn the product orientation demo - repurpose script |  |  | 3 hours
|  | Test run - orientation (with portal and product demo (record each)) |  |  | 1 hour
|  | Know how the reseller will place the order |  |  | 30 min
|  | Determine system for reseller orientation (Skype, GoToMeeting/GoToWebinar, etc.) |  |  | 30 min
|  | Conduct orientation with each partner (1 on 1, webinars) - follow reseller worksheet |  |  | 1 hour each
Enablement
|  | Create reseller SEO - landing page template |  |  | 3 hours
|  | Create reseller email template |  |  | 3 hours
|  | Repurpose the lead referral template |  |  | 2 hours
|  | Setup marketing meeting with reseller |  |  | 15 min each
|  | Conduct marketing meeting (setup 3 promos (setup promo calendar)) |  |  | 20 min each
|  | Conduct marketing meeting - SEO landing page template, email campaign |  |  | 1 hour setup
2nd Setup
|  |  | Confirm reseller has product listed on website |  | 10 min
|  |  | Add reseller to reseller locator (within portal) |  | 10 min
|  |  | Send email to reseller confirming now listed in locator |  | 10 min
|  | Create thank you email - for reseller's first sale, send to reseller |  |  | 10 min
|  | Create thank you email for 2nd sale - send to reseller |  |  | 10 min
|  | Create newsletter template, send monthly newsletter (informatl) |  |  | 1 hour
|  | Setup levels, certification, quotas |  |  | 6 months later
Define reseller levels (usually at 6 month mark)
|  |  |  | Review existing reseller sales, determine break points | 1 hour
Define certification program
|  |  |  | Review reseller FAQs, additional training areas | 2 hours
|  |  |  | Determine how to train/certifiy resellers | 1 hour
|  |  |  | Determine systems to use (LMS) | 1 hour | Learn
|  |  |  | Create training material (PowerPoint, manuals) | 3 months
|  |  | Create reseller levels and certification policies |  | 3 months
|  |  | Create reseller email to announce program |  | 1 hour
|  |  | Setup meeting with ALL partners (1 on 1, group webinars) to review new levels and certification |  | 1 hour
|  |  | Conduct partner meetings (with EVERY partner) - use worksheet to confirm attendance |  | 1 hour
Channel Management – Ongoing motivation
Three phases of a new reseller
Creating loyalty within the channel
What works – spiffs, rebates, contest, NFR’s
Field Management – model calls & coaching calls
The Game of Work – tracking
Integration – inside sales, field sales, FAE’s, channel sales
Channel maturity – weeding out non-producers
Increasing dedication & barriers to entry
Refining Your Program – Putting It All Together
Creating & leveraging a reseller partner council
Ongoing recruiting – replacing non-producers
The plan of action – details with timelines
Q & A to address all remaining channel questions
Channel Operations
CRMs, PRMs, other Software
Industry ratios, time lines, expectations
Channel Collateral (PowerPoints, Competitive Matrix, Price List, Policies (lead, deal reg, NFR, etc.), Agreement
Resources (websites, rep firms (Retail to System Integrator), software, research, publications, consultants, partner promotions, reseller training, etc.

## Instructions
Copyright © 2019, Chanimal™, all rights reserved. Also licensed to SaaSMAX.
The checklist helps ensure you complete ALL of the definition, recruiting, orientation and enablement
steps to create a world-class reseller partner program.
More detail can be found in your master plan of action.