## Program Checklist
Reseller Program Checklist
| Category |  |  |  | Time Frame | Schedule | Assigned To | Notes
Status | Program Definition & Setup
|  | Define program (levels, agreement, policies) |  |  | 1 hour
|  | Setup Portal | [5 empty] | See Portal Checklist for additional details
|  |  | Install Wordpress (fresh install) |  | 30 min
|  |  | Clone portal |  | 45 min
|  |  | Personalize - logo, etc. (see portal checklist) |  | 1 hour
|  |  | Setup emails and phone (partners@company.com), separate phone line |  | 30 min
|  |  | Test portal (ALL forms) |  | 30 min
|  | Setup policies (review & edit every page of portal) |  |  | 2 hours
|  | Create SaaSMAX Profile (if applicable) and Ideal Partner Configuration |  |  | 2 hours
|  | Create outstanding deliverables for portal |  |  | Varies
|  |  | Competitive Matrix |  | 3 weeks |  |  | If don't have one
|  |  | Persuasive document |  | 3 days
|  |  | PowerPoint |  | 1 day - 1 week |  |  | Time dependant on persuasive doc
|  |  | 25/50/100 word description |  | 2 hours
|  |  | Market Info |  | 2 hours
|  |  | Logo, graphics |  | 30 min
|  |  | Price list (PDF) |  | 1 hour
|  |  | Create product demo script |  | 4 hours
|  |  | Other (white papers, case studies, videos) |  | Varies
|  | Review EVERY page of portal site - confirm it is complete |  |  | 1 hour
|  | Determine reseller margin & how will get paid |  |  | 2 hours
|  | Confirm the system and process for partner payments |  |  | 1 hour
|  | Create reseller approval email |  |  | 1 hour
|  | Create recruiting emails (for previous interest, new, competititors) |  |  | 2 hours
|  | Create orientiaton demo script |  |  | 5 min
|  | Determine NFR process (how to get partner license #'s) |  |  | 1 hour
|  | Confirm the WordPress master user email is switched to your partner@ email |  |  | 5 min
|  | Confirm Zendesk chat has been switched to partner@email - shows traffic at portal site |  |  | 10 min
|  | Put a link to reseller portal / application from main site - ready to recruit |  |  | 10 min
Recruiting
|  | Complete SaaSMAX IPC (Ideal Partner Configuration) |  |  | 15 min |  |  | info.saasmax.com/ideal-partner-configuration-form
Database
|  |  | Compile list of any previously interested partners |  | 1 hour
|  |  | Compile Chanimal database |  | 1 hour
|  |  | Compile competitors resellers (internal & Navin) |  | 1 week |  |  | A counter-strike - weakens their program, strengthens yours
|  |  |  | Finalize reseller database fields (Chanimal sample) | 3 hours
Systems
|  |  | Determine CRM systems or spreadsheet |  | 1 hour
|  |  | Mass email system - select & setup |  | 2 hours
|  |  | Import database(s) into email system |  | 1 hour
|  |  | Setup recruiting email template(s) |  | 30 min
|  |  | Call our phone numbers, send ourselves emails - confirm they are all active |  | 15 min
|  |  | Confirm channel people are getting the emails from the partner FORMS |  | 15 min
Email campaign
|  |  | Determine when it will go out (days and times (typically work hours)) |  | 30 min
|  |  | Start first email |  | 30 min
|  |  | Clean out bounce backs, remove names, applied/responded |  | 2 hours
|  |  | Start 2nd email |  | 30 min
|  |  | Clean out bounce backs, remove names, applied/responded |  | 1 hour
|  |  | Start 3rd email |  | 30 min
|  |  | Clean out bounce backs, remove names, applied/responded |  | 1 hour
|  | Program Press Release (create and send) |  |  | 3 hours
Portal Training
|  |  | Wordpress overview & training (if don't know how to edit) - YouTube |  | 3 hours
|  |  | Know how to add reseller |  | 30 min
|  |  | Know how to manage forum |  | 1 hour
|  |  | Can add a page, set permissions |  | 30 min
|  |  | Can add a contact to reseller locator |  | 15 min
|  | Finalize Reseller Follow-up Worksheet |  |  | 30 min
Set up new resellers
|  |  | Get NFR information |  | 15 min
|  |  | Add reseller to portal (will send out email) |  | 15 min
|  |  | Determine webinar date |  | 15 min
|  |  | Edit approval email (NFR, password, webinar date) and send |  | 15 min
Orientation
|  | Learn the product |  |  | 6 hours
|  | Learn the product demo script |  |  | 3 hours
|  | Learn the product orientation demo - repurpose script |  |  | 3 hours
|  | Test run - orientation (with portal and product demo (record each)) |  |  | 1 hour
|  | Know how the reseller will place the order |  |  | 30 min
|  | Determine system for reseller orientation (Skype, GoToMeeting/GoToWebinar, etc.) |  |  | 30 min
|  | Conduct orientation with each partner (1 on 1, webinars) - follow reseller worksheet |  |  | 1 hour each
Enablement
|  | Create reseller SEO - landing page template |  |  | 3 hours
|  | Create reseller email template |  |  | 3 hours
|  | Repurpose the lead referral template |  |  | 2 hours
|  | Setup marketing meeting with reseller |  |  | 15 min each
|  | Conduct marketing meeting (setup 3 promos (setup promo calendar)) |  |  | 20 min each
|  | Conduct marketing meeting - SEO landing page template, email campaign |  |  | 1 hour setup
2nd Setup
|  |  | Confirm reseller has product listed on website |  | 10 min
|  |  | Add reseller to reseller locator (within portal) |  | 10 min
|  |  | Send email to reseller confirming now listed in locator |  | 10 min
|  | Create thank you email - for reseller's first sale, send to reseller |  |  | 10 min
|  | Create thank you email for 2nd sale - send to reseller |  |  | 10 min
|  | Create newsletter template, send monthly newsletter (informatl) |  |  | 1 hour
|  | Setup levels, certification, quotas |  |  | 6 months later
Define reseller levels (usually at 6 month mark)
|  |  |  | Review existing reseller sales, determine break points | 1 hour
Define certification program
|  |  |  | Review reseller FAQs, additional training areas | 2 hours
|  |  |  | Determine how to train/certifiy resellers | 1 hour
|  |  |  | Determine systems to use (LMS) | 1 hour | Learn
|  |  |  | Create training material (PowerPoint, manuals) | 3 months
|  |  | Create reseller levels and certification policies |  | 3 months
|  |  | Create reseller email to announce program |  | 1 hour
|  |  | Setup meeting with ALL partners (1 on 1, group webinars) to review new levels and certification |  | 1 hour
|  |  | Conduct partner meetings (with EVERY partner) - use worksheet to confirm attendance |  | 1 hour
Channel Management – Ongoing motivation
Three phases of a new reseller
Creating loyalty within the channel
What works – spiffs, rebates, contest, NFR’s
Field Management – model calls & coaching calls
The Game of Work – tracking
Integration – inside sales, field sales, FAE’s, channel sales
Channel maturity – weeding out non-producers
Increasing dedication & barriers to entry
Refining Your Program – Putting It All Together
Creating & leveraging a reseller partner council
Ongoing recruiting – replacing non-producers
The plan of action – details with timelines
Q & A to address all remaining channel questions
Channel Operations
CRMs, PRMs, other Software
Industry ratios, time lines, expectations
Channel Collateral (PowerPoints, Competitive Matrix, Price List, Policies (lead, deal reg, NFR, etc.), Agreement
Resources (websites, rep firms (Retail to System Integrator), software, research, publications, consultants, partner promotions, reseller training, etc.

## Portal Checklist
Partner Portal Setup
| Category |  |  |  |  | Time Frame | Schedule | Assigned To | Notes
Status | Program Definition & Setup
|  | Define program (levels, agreement, type, policies) |  |  |  | 1 hour
Setup Portal
|  |  | Sign up for ISP (Cloudways.com ($10/month) recommended) - unless have one |  |  | 10 min |  |  | Do not use GoDaddy, do not setup a Multi-site install, no passwords or staging site (must be live to start)
|  |  | Create domain name (CompanyPartners.com), or create sub-directory YourDomain.com/Partners |  |  | 10 min
|  |  | Install Wordpress (fresh install) |  |  | 10 min |  |  | Do not use a multi-site install (some plugins don't work). Use a fresh Wordpress install.
|  |  | Clone portal |  |  | 15 min |  |  | Ted will clone it over - about 10 minutes
Note: please do not modify anything until setup is complete & backed up
|  |  | Update all plugins |  |  | 5 min
|  |  | Remove plugins that don't apply (LeadSmart, WP Engine, Hello Dolly) |  |  | 5 min
|  |  | Decide & submit channel manager name, title, phone & email (partners@company.com) |  |  | 5 min |  |  | Do not use actual email (use a "role-based" partners@), then have IT redirect it to your personal email.
|  |  | Decide which home page (home or home affiliate) |  |  | 1 min
|  |  | If affiliate, add Referral Partner tab to home and internal agreement page |  |  | 10 min
|  |  | Modify look and feel |  |  | 20 min
|  |  | Add logo & customize LoginPress (colors, background) |  |  | 1 hour
|  |  | Decide if and which social icons (add URLs) |  |  | 10 min
Personalize
|  |  |  | Resize and add white space and logo to theme |  | 10 min
|  |  |  | Add company Favicon |  | 5 min
|  |  |  | Search & Replace |  |  |  |  | Use Tools/ Better Search & Replace. Remember to untick the last box to complete the replacement.
[5 empty] | Channel Manager Name | 5 min |  |  | Need to know the PRIMARY contact (even if you have multiple)
[5 empty] | Phone | 5 min
[5 empty] | Email | 5 min |  |  | partners@YourCompany.com (never give personal email--hard to turn off later. Use a role-based email.
[5 empty] | Title | 5 min
|  |  |  | Add photo of Channel Manager (external page, internal home page) |  | 10 min |  |  | A square photo 180x180 is the default size
|  |  | Submit preferred company address |  |  | 5 min
|  |  | Update address on footer and contact us page |  |  | 5 min |  |  | Go to Appearance / Widgets / Footer 1-4 to change contact info
|  |  | Confirm Header - HOME page link is working |  |  | 5 min |  |  | Returns to company home page. Found in the header (secondary) menu
|  |  | Update Copyright - name and year (footer) |  |  | 2 min |  |  | See documentation
|  |  | Select which Partner Levels to use (Referrals/Reseller/OEM). Change table number in both places. |  |  | 5 min
|  |  | Map Partner Level colors to site colors |  |  | 10 min
|  |  | Setup captia w/Google |  |  | 15 min
|  |  | Add Captia to Gravity Forms |  |  | 5 min
|  |  | Add Captia to Membership Pro |  |  | 5 min |  |  | Page 23 of documentation - "Google API Keys"
|  |  | Setup Google maps (create project, then add maps info) - has to be tied to company URL |  |  | 20 min
|  |  | Add Server Code to Maps |  |  | 5 min
|  |  | Change Settings Master email (should be partners@company.com) |  |  | 10 min
|  |  | Change Master User email |  |  | 5 min
|  |  | Confirm master email is being received |  |  | 5 min
|  |  | Fix email if not being received (WP SMTP) |  |  | 20 min
|  |  | Content updates | [5 empty] | Typically done in two meetings
|  |  |  | Review & edit every policy on every page |  | 2 hours
[5 empty] | Reseller agreement | 40 min
[5 empty] | Affiliate agreement | 40 min |  |  | No affiliate, no deal reg if retail, etc.
|  |  | Turn off non-applicable menus, or modify and re-arrange |  |  | 30 min |  |  | Do NOT remove until you understand profiling
Review & edit every applicable form
|  |  |  | Contact Me |  | 10 min
|  |  |  | Deal Register |  | 10 min
|  |  |  | MDF Request form |  | 10 min
|  |  |  | NFR Quiz |  | 10 min
|  |  |  | Place Order |  | 10 min
|  |  |  | Referral Form |  | 10 min
|  |  |  | Referral Partner Application - ensure partner agreement is in form |  | 15 min
|  |  |  | Reseller Application - ensure partner agreement is in form |  | 15 min
|  |  |  | Need other forms? Distributor (so they are in the system) |  | 20 min |  |  | PHP is the default WordPress email--but may have to use SMTP for better deliverability
|  |  | Test every form (consider SMTP email - if not setup by ISP) |  |  | 20 min
Chat Setup
|  |  |  | Switch user (login to Zendesk for free account, use new login) |  | 10 min |  |  | Found in Custom HTML section of Footer 4
|  |  |  | Edit in Plugin or in Widgets area |  | 10 min |  |  | Allows you to see who is on your site, plus you can support via mobile text
|  |  |  | Download and setup mobile Zendesk app |  | 10 min
|  |  |  | Confirm emails and chat messages are arriving |  | 10 min
|  |  |  | Other chat (if not using Zendesk), reporting |  | 20 min
|  |  | Affiliate Setup | [5 empty] | Site Licence resides with Chanimal - site must be added to activate software
|  |  |  | Add URL to the WPAffiliate site - register URL |  | 10 min
Determine program elements
[5 empty] | Commission | 20 min
[5 empty] | How to pay | 10 min
[5 empty] | System to pay | 5 min
[5 empty] | Privacy policy | 10 min
[5 empty] | Create initial banner | 1 hour
[5 empty] | Edit copy sections | 40 min
[5 empty] | Create affiliate sample landing page | 5 hours
|  |  |  | Setup Captia (Affiliate/Settings/Misc) - use existing from Gravity Forms |  | 5 min
|  |  |  | Confirm Default Referral URL (Affiliate/Settings/Misc) |  | 5 min |  |  | Create new login for Wordfence (free). Or it sends all updates to me--not you. | 6bf804783708a845be12e64498c04fce00c68cb3203f946a4db53f7f9217f0348b22833ae06d2b085a7ad39a5a256228f5b0791fbeab9eff6dc1c6efd738bff577b9932c7c903fefe9f73f975fd75f5c56ba04b19820a6fa3f05529d9f631bd1
|  |  |  | Setup server exclusions so visitor cookies work |  | 15 min |  |  | VARNISH settings. Exclude the URL. Exclude these cookies: affwp_ref , affwp_ref_visit_id , affwp_campaign. See portal documentation.
|  |  | Wordfence Security - new login |  |  | 5 min
|  |  | LMS - Add the "Learn the Product" Section to the sales lesson |  |  | 1 hour
|  |  | Newsletter - update dates for the first 3 posts |  |  | 6 min
Integrations
CRM / Marketing Automation
[5 empty] | Install plugin | 20 min
[5 empty] | Map fields | 20 min
[5 empty] | Test bi-directional | 10 min
Note: some plugins may require 3rd party upgrades that are not part of the normal portal
|  |  | Back up site (Updraft Plus - Settings) |  |  | 5 min
CONTINUE with the Program Checklist

## Instructions
Copyright © 2019, Chanimal™, all rights reserved. Also licensed to SaaSMAX.
The checklist helps ensure you complete ALL of the definition, recruiting, orientation and enablement
steps to create a world-class reseller partner program.
More detail can be found in your master plan of action.